## Test protocol 1
Test case | Resource id | HAC resource name | BDN node | Fault injection time | Start time | End time | Actual outcome description | Actual outcome | Expected outcome | Remark | Difference start-end | Resource | RG | System | HAC detection window | HAC resource reinitialization window | HAC resource group failover window | HAC system failover window | BPF preparation window for resource | BDN-HAC detection window for resource | Monitor interval | BDN input | BDN inference | BDN output | Total
T1 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-02-22 16:21 | 2021-02-22 16:22 | 2021-02-22 16:22 | Restarted automatically by the application | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  | 0:00 | 0:00 | 60 | 0:00 | 0:00 | 0:00 | 0:00
T2 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-02-09 01:58 | 2021-02-09 01:59 | 2021-02-09 02:13 | Resource group failed over | RG failover | No failure | RG | 0:14 |  | 0:14 |  | 0:01 |  | 0:14 |  |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T3 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-01 02:54 | 2021-03-01 02:54 | 2021-03-01 03:02 | Restarted by the cluster | No failure | No failure | Resource | 0:08 | 0:01 |  |  | 0:00 | 0:01 |  |  |  | 0:00 | 120 | 0:00 | 0:00 | 0:00 | 0:00
T3 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-01 03:03 | 2021-03-01 03:03 | 2021-03-01 03:07 | Restarted by the cluster | No failure | No failure | Resource | 0:04 | 0:01 |  |  | 0:00 | 0:01 |  |  |  | 0:00 | 120 | 0:00 | 0:00 | 0:00 | 0:00
T4 | C1G2A1B1 | rsc_DEV_database | database | 2021-02-09 20:22 | 2021-02-09 20:23 | 2021-02-09 20:35 | The complete system failed over | System failover | No failure | System | 0:12 |  |  | 0:12 | 0:01 |  |  | 0:12 |  | 0:00 | 120 | 0:00 | 0:00 | 0:00 | 0:00
T5 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-08 21:38 | 2021-03-08 21:38 | 2021-03-08 21:49 | Complete failover | System failover | RG failover | System | 0:11 |  |  | 0:11 | 0:00 |  |  | 0:11 |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T5 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-08 21:38 | 2021-03-08 21:38 | 2021-03-08 21:49 | The process was killed when the file system was removed forcefully. Restarted automatically. The two file systems were unmounted and mounted again | No failure | No failure | Resource | 0:11
T6 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-01 00:11 | 2021-03-01 00:12 | 2021-03-01 00:14 | The related process was restarted automatically | No failure | No failure | Resource | 0:03 | 0:01 |  |  | 0:01 | 0:01 |  |  |  | 0:00 | 60 | 0:00 | 0:00 | 0:00 | 0:00
T6 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-01 00:33 | 2021-03-01 00:33 | 2021-03-01 00:34 | The file system was unmounted but mounted again automatically | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T7 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS trans | 2021-03-01 00:45 | 2021-03-01 00:45 | 2021-03-01 00:45 | The file system was unmounted but mounted again automatically. The resource rec_DEV_ASCS was also restarted | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T7 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-01 00:45 | 2021-03-01 00:45 | 2021-03-01 00:45 | The file system was unmounted but mounted again automatically. The resource rec_DEV_ASCS was also restarted | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T8 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-08 22:45 | 2021-03-08 22:45 | 2021-03-08 22:56 | The complete system failed over | System failover | RG failover | System | 0:12 |  |  | 0:12 | 0:00 |  |  | 0:12 |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T8 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-08 22:45 | 2021-03-08 22:45 | 2021-03-08 22:56 |  | Above | [12 empty] | 60
T9 | C1G5A1B1 | dlm_DEV | DLM | 2021-03-01 03:19 | 2021-03-01 03:20 | 2021-03-01 03:40 | The node is rebooted | System failover | System failover | System | 0:20 |  |  | 0:20 | 0:01 |  |  | 0:20 |  | 0:00 | 60 | 0:00 | 0:00 | 0:00 | 0:00
[11 empty] | 0:00 |  |  |  | 0:00 |  |  |  |  | 0:00 |  | 0:00 | 0:00 | 0:00 | 0:00
T1 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-01 04:14 | 2021-03-01 04:14 | 2021-03-01 04:15 | Restarted automatically by the application | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 60 | 0:00 | 0:00 | 0:00 | 0:00
T2 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-01 04:26 | 2021-03-01 04:26 | 2021-03-01 04:26 | Restarted by the cluster but the related service was also restarted | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T3 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-01 04:29 | 2021-03-01 04:30 | 2021-03-01 04:32 | Restarted by the cluster | No failure | No failure | Resource | 0:01 | 0:01 |  |  | 0:00 | 0:01 |  |  |  | 0:00 | 120 | 0:00 | 0:00 | 0:00 | 0:00
T3 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-01 04:32 | 2021-03-01 04:35 | 2021-03-01 04:36 | Restarted by the cluster | No failure | No failure | Resource | 0:02 | 0:01 |  |  | 0:01 | 0:01 |  |  |  | 0:00 | 120 | 0:00 | 0:00 | 0:00 | 0:00
T4 | C1G2A1B1 | rsc_DEV_database | database | 2021-03-01 04:46 | 2021-03-01 04:48 | 2021-03-01 04:53 | Restarted by the cluster | System failover | No failure | System | 0:05 |  |  | 0:05 | 0:02 |  |  | 0:05 |  | 0:00 | 120 | 0:00 | 0:00 | 0:00 | 0:00
T5 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-08 21:50 | 2021-03-08 21:50 | 2021-03-08 22:02 | The service group failed over and the server was rebooted | System failover | RG failover | System | 0:12 |  |  | 0:12 | 0:00 |  |  | 0:12 |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T5 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-08 21:50 | 2021-03-08 21:50 | 2021-03-08 22:02 | The service group failed over and the server was rebooted | Above | No failure
T6 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-01 11:14 | 2021-03-01 11:15 | 2021-03-01 11:15 | The service was started even before the failure was captured by the monitoring service | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:01 | 0:00 |  |  |  | 0:00 | 60 | 0:00 | 0:00 | 0:00 | 0:00
T6 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-01 11:15 | 2021-03-01 11:15 | 2021-03-01 11:15 | The file system was remounted automatically | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T7 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS trans | 2021-03-01 11:57 | 2021-03-01 11:57 | 2021-03-01 11:58 | File system was mounted by the cluster | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T7 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-01 11:57 | 2021-03-01 11:57 | 2021-03-01 11:58 | File system was mounted by the cluster | No failure | No failure | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T8 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-08 22:57 | 2021-03-08 22:57 | 2021-03-08 23:08 | The complete system failed over | System failover | RG failover | System | 0:11 |  |  | 0:11 | 0:00 |  |  | 0:11 |  | 0:00 | 20 | 0:00 | 0:00 | 0:00 | 0:00
T8 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-08 22:57 | 2021-03-08 22:57 | 2021-03-08 23:08 |  | Above | No failure | [11 empty] | 120
T9 | C1G5A1B1 | dlm_DEV | DLM | 2021-03-03 10:57 | 2021-03-03 11:00 | 2021-03-03 11:40 | Complete failover | System failover | System failover | System | 0:41 |  |  | 0:41 | 0:03 |  |  | 0:41 |  | 0:00 | 60 | 0:00 | 0:00 | 0:00 | 0:00

## Test protocol 2
Test case | Resource id | HAC resource name | BDN node | Fault injection time | Start time | End time | Actual outcome description | Actual outcome | Expected outcome | Remark |  | Difference start-end | Resource | RG | System | HAC detection window | HAC resource reinitialization window | HAC resource group failover window | HAC system failover window | BPF preparation window for resource | BDN-HAC detection window for resource | BDN input | BDN inference | BDN output | Total
T1 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-06 01:00 | 2021-03-06 01:02 | 2021-03-06 01:02 | 00:59:55 and 01:02:30 5 times. Restarted automatically by the application and then one time by the HAC, and then again by the application | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T2 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-05 11:48 | 2021-03-05 11:48 | 2021-03-05 11:48 | Automatically mounted | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T3 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-06 00:43 | 2021-03-06 00:45 | 2021-03-06 00:47 | Between 00:43:05 and 00:44:19 5 times. The entire resource group was restated. No failover | No failure | No failure |  | Resource | 0:01 | 0:01 |  |  | 0:00 | 0:01 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T4 | C1G2A1B1 | rsc_DEV_database | database | 2021-03-05 14:11 | 2021-03-05 14:20 | 2021-03-05 14:22 | Dependent ASCS and CI were also quickly restarted | No failure | No failure |  | Resource | 0:02 | 0:02 |  |  | 0:02 | 0:02 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T5 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-09 08:20 | 2021-03-09 08:20 | 2021-03-09 08:42 | System failover | System failover | RG failover |  | System | 0:22 |  |  | 0:22 | 0:00 |  |  | 0:22 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service |  |  |  | The system failed over before the test case could be executed
T6 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-09 08:45 | 2021-03-09 08:46 | 2021-03-09 08:54 | Restarted automatically by the application | No failure | No failure |  | Resource | 0:09 | 0:09 |  |  | 0:00 | 0:09 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-09 08:45 | 2021-03-09 08:46 | 2021-03-09 08:54 | Initialised automatically by the HAC | No failure | No failure |  | Resource | 0:09 | 0:09 |  |  | 0:00 | 0:09 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T7 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS trans | 2021-03-05 17:53 | 2021-03-05 17:53 | 2021-03-05 17:53 | Initialised automatically by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-05 17:53 | 2021-03-05 17:53 | 2021-03-05 17:53 | Initialised automatically by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T8 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-09 09:03 | 2021-03-09 09:04 | 2021-03-09 09:18 | System failover. Both nodes rebooted | System failover | RG failover |  | System | 0:14 |  |  | 0:14 | 0:00 |  |  | 0:14 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-09 09:03 | 2021-03-09 09:04 | 2021-03-09 09:18 | Above
T9 | C1G5A1B1 | dlm_DEV | DLM | 2021-03-05 22:42 | 2021-03-05 22:45 | 2021-03-05 22:55 | Complete failover | System failover | System failover |  | System | 0:10 |  |  | 0:10 | 0:04 | 0:00 | 0:00 | 0:10 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
[21 empty] | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T1 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-05 23:32 | 2021-03-05 23:34 | 2021-03-05 23:35 | Resulted in failure of fs_3_DEV_ASCS and fs_2_DEV_ASCS. Only after 10 fault injection, there was a delay and failure notification was created so that HAC could initiate the resource and the two child nodes | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T2 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-06 00:20 | 2021-03-06 00:20 | 2021-03-06 00:20 | Reinitiated automatically be the HAC. The service rsc_DEV_ASCS00 was also reinitialised briefly | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T3 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-06 00:28 | 2021-03-06 00:30 | 2021-03-06 00:38 | Between 00:28:14 and 00:29:10 5 times. The entire resource group failed over to the secondary node. | RG failover | No failure |  | RG | 0:02 |  | 0:02 |  | 0:00 |  | 0:02 |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T4 | C1G2A1B1 | rsc_DEV_database | database | 2021-03-06 01:08 | 2021-03-06 01:09 | 2021-03-06 01:12 | Dependent ASCS and CI were also quickly restarted | No failure | No failure |  | Resource | 0:03 | 0:03 |  |  | 0:02 | 0:03 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T5 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-06 01:18 | 2021-03-06 01:18 | 2021-03-06 02:37 | System failover. Both nodes are failed over | System failover | RG failover |  | System | 1:19 |  |  | 1:19 | 0:01 |  |  | 1:19 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-06 01:18 | 2021-03-06 01:18 | 2021-03-06 02:37 | System failover. Both nodes are failed over |  | No failure
T6 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-06 02:40 | 2021-03-06 02:40 | 2021-03-06 02:40 | Restarted automatically by the application | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-06 02:40 | 2021-03-06 02:40 | 2021-03-06 02:40 | Reinitialised by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T7 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS trans | 2021-03-06 02:45 | 2021-03-06 02:45 | 2021-03-06 02:45 | Reinitialised by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-06 02:45 | 2021-03-06 02:45 | 2021-03-06 02:45 | Reinitialised by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T8 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-06 02:49 | 2021-03-06 02:49 | 2021-03-06 03:06 | System failover. Both nodes failed | System failover | RG failover |  | System | 0:17 |  |  | 0:17 | 0:00 |  |  | 0:17 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-08 22:57
T9 | C1G5A1B1 | dlm_DEV | DLM | 2021-03-06 04:14 | 2021-03-06 04:15 | 2021-03-06 06:02 | System failover | System failover | System failover |  | System | 1:48 |  |  | 1:48 | 0:01 |  |  | 1:48 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
[21 empty] | 86400 | 0:00
0.43
0:00

## Test protocol 3
Test case | Resource id | HAC resource name | Name | Fault injection time | Start time | End time | Actual outcome description | Actual outcome | Expected outcome | Remark |  | Difference start-end | Resource | RG | System | HAC detection window | HAC resource reinitialization window | HAC resource group failover window | HAC system failover window | BPF preparation window for resource | BDN-HAC detection window for resource | BDN input | BDN inference | BDN output | Total
T10 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-08 00:35 | 2021-03-08 00:35 | 2021-03-08 00:36 | 5 executions between 00:34:40 and 00:36:08. All were restarted by the application | No failure | No failure | Node 2 | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T11 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-08 00:39 | 2021-03-08 00:39 | 2021-03-08 00:39 | The file system was remounted by the HAC upon detection of the failure | No failure | No failure | Node 2 | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T12 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-08 00:43:32 | 2021-03-08 00:44 | 2021-03-08 00:53 | Node fencing and complete restart of the node | System failover | RG failover | Node 2 | System | 0:09 |  |  | 0:09 | 0:00 |  |  | 0:09 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T13 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-08 01:25 | 2021-03-08 01:25 | 2021-03-08 01:26 | 5 executions between 01:24:38 and 01:26:12. All were remounted by the HAC | No failure | No failure | Node 2 | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T14 | C1G2A1B1C1 | fs_DEV_database | FS database | 2021-03-08 07:08 | 2021-03-08 07:09 | 2021-03-08 07:24 | Complete System failover and the node was restarted | System failover | RG failover | Node 1 | System | 0:14 |  |  | 0:14 | 0:02 |  |  | 0:14 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T15 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-08 08:22 | 2021-03-08 08:23 | 2021-03-08 08:39 | Removing the file system forcibly caused the system failover |  |  | Node 1
T15 | C1G3A1B1C1 | fs_DEV_CI | FS main instance | 2021-03-08 08:22 | 2021-03-08 08:23 | 2021-03-08 08:39 | Complete System failover and the node was restarted | System failover | RG failover | Node 1 | System | 0:16 |  |  | 0:16 | 0:00 |  |  | 0:16 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T16 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-09 12:21 | 2021-03-09 12:21 | 2021-03-09 12:39 | Complete System failover and the node was restarted | System failover | RG failover |  | System | 0:18 |  |  | 0:18 | 0:00 |  |  | 0:18 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-09 12:21 | 2021-03-09 12:21 | 2021-03-09 12:39 |  |  | No failure
T17 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-08 08:46 | 2021-03-08 08:46 | 2021-03-08 08:46 | The resource was automatically remounted by the HAC | No failure | No failure | Node 2 | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  | 0:00 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T7 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-08 08:46 | 2021-03-08 08:46 | 2021-03-08 08:46 | The resource was automatically remounted by the HAC | No failure | No failure | Node 2 | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T18 | C1G3A1B1C1 | fs_DEV_CI | FS main instance | 2021-03-08 08:52 | 2021-03-08 08:52 | 2021-03-08 09:17 | Complete System failover and the node was restarted | System failover | RG failover |  | System | 0:24 |  |  | 0:24 | 0:00 |  |  | 0:24 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T18 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-08 08:52 | 2021-03-08 08:55 | 2021-03-08 09:17 | The file system removal caused the system to fail over
T19 | C1G5A1B2 | fs_DEV_sapmnt | FS DLM | 2021-03-08 10:19 | 2021-03-08 10:19 | 2021-03-08 10:19 | The file system was remounted by the HAC upon detection | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:01 | 0:00 |  | 0:00 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
0:00
T10 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-08 11:23 | 2021-03-08 11:23 | 2021-03-08 11:24 | 5 executions between 11:22:52 and 11:23:40 All were restarted by the application | No failure | No failure | Node 2 | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T11 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-08 13:06 | 2021-03-08 13:06 | 2021-03-08 13:07 | The file system was remounted by the HAC upon detection | No failure | No failure | Node 2 | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T12 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-08 13:14 | 2021-03-08 13:14 | 2021-03-08 13:18 | Complete System failover and the node was restarted | System failover | RG failover | Node 2 | System | 0:04 |  |  | 0:04 | 0:00 |  |  | 0:04 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T13 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-09 11:18 | 2021-03-09 11:18 | 2021-03-09 11:20 | 5 executions between 11:17:36 and 11:19:35. All were remounted by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T14 | C1G2A1B1C1 | fs_DEV_database | FS database | 2021-03-08 13:36 | 2021-03-08 13:36 | 2021-03-08 13:53 | Complete System failover and the node was restarted | System failover | RG failover | Node 1 | System | 0:17 |  |  | 0:17 | 0:00 |  |  | 0:17 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T15 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-08 14:20 | 2021-03-08 14:19 | 2021-03-08 14:36 | The removal of the file system caused the system to failover |  | No failure | Node 1
T15 | C1G3A1B1C1 | fs_DEV_CI | FS main instance | 2021-03-08 14:21 | 2021-03-08 14:23 | 2021-03-08 14:36 | Complete System failover and the node was restarted | System failover | RG failover | Node 1 | System | 0:13 |  |  | 0:13 | 0:02 |  |  | 0:13 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T16 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-08 14:58 | 2021-03-08 14:58 | 2021-03-08 15:08 | Complete System failover and the node was restarted | System failover | RG failover | Node 1 | System | 0:11 |  |  | 0:11 | 0:00 | 0:00 |  | 0:11 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-08 14:58 | 2021-03-08 14:59 | 2021-03-08 15:08 | [9 empty] | 0:01 | 0:00 |  | 0:00 |  |  | 0:00 | 0:00 | 0:00 | 0:00
T17 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-08 15:13 | 2021-03-08 15:13 | 2021-03-08 15:14 | The resource was automatically remounted by the HAC | No failure | No failure | Node 2 | Resource | 0:01 | 0:01 |  |  | 0:00 | 0:01 |  | 0:00 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-08 15:13 | 2021-03-08 15:13 | 2021-03-08 15:14 | The resource was automatically remounted by the HAC | No failure | No failure | Node 2 | Resource | 0:01 | 0:01 |  |  | 0:00 | 0:01 |  | 0:00 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T18 | C1G3A1B1C1 | fs_DEV_CI | FS main instance | 2021-03-08 15:25 | 2021-03-08 15:25 | 2021-03-08 15:36 | Complete System failover and the node was restarted | System failover | RG failover |  | System | 0:11 |  |  | 0:11 | 0:00 | 0:00 |  | 0:11 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T18 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-08 15:25 | 2021-03-08 15:27 | 2021-03-08 15:36 | Complete System failover and the node was restarted
T19 | C1G5A1B2 | fs_DEV_sapmnt | FS DLM | 2021-03-08 12:05 | 2021-03-08 12:05 | 2021-03-08 12:05 | The file system was remounted by the HAC upon detection | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00

## Test protocol 4
Test case | Resource id | HAC resource name | Name | Fault injection time | Start time | End time | Actual outcome description | Actual outcome | Expected outcome | Remark |  | Difference start-end | Resource | RG | System | HAC detection window | HAC resource reinitialization window | HAC resource group failover window | HAC system failover window | BPF preparation window for resource | BDN-HAC detection window for resource | BDN input | BDN inference | BDN output | Total
T10 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-06 04:37 | 2021-03-06 04:37 | 2021-03-06 04:40 | 5 times 04:38:32 and 04:39:18. The first ones were restarted by the application, and one restart by the HAC |  |  |  | Resource | 0:01 | 0:01 |  |  | 0:00 | 0:01 |  | 0:00 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T11 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-07 00:56 | 2021-03-07 00:56 | 2021-03-07 00:56 | Automatically restarted by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T12 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-07 01:16 | 2021-03-07 01:17 | 2021-03-07 01:42 | Resulting in failure of the node is fenced and complete system restart | System failover | RG failover |  | System | 0:26 |  |  | 0:26 | 0:00 |  |  | 0:26 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T13 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-07 02:48 | 2021-03-07 02:49 | 2021-03-07 02:50 | The resource is restarted by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T14 | C1G2A1B1C1 | fs_DEV_database | FS database | 2021-03-07 03:33 | 2021-03-07 03:33 | 2021-03-07 03:58 | System failover. The node was fenced. | System failover | RG failover |  | System | 0:26 |  |  | 0:26 | 0:00 |  |  | 0:26 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T15 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-07 04:35 | 2021-03-07 04:36 | 2021-03-07 04:49 | System failover. The node was fenced. | System failover | RG failover
T15 | C1G3A1B1C1 | fs_DEV_CI | FS main instance | 2021-03-07 04:35 | 2021-03-07 04:36 | 2021-03-07 04:49 | System failover. The node was fenced. | System failover | RG failover |  | System | 0:13 |  |  | 0:13 | 0:00 |  |  | 0:13 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T16 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-07 05:05 | 2021-03-07 05:05 | 2021-03-07 05:16 | System failover. The node was fenced. | System failover | RG failover |  | System | 0:12 |  |  | 0:12 | 0:00 |  |  | 0:12 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T16 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-07 05:04:36 | 2021-03-07 05:05 | 2021-03-07 05:16 | System failover. The node was fenced. | [13 empty] | 0:00
T17 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-07 05:26 | 2021-03-07 05:26 | 2021-03-07 05:26 | The resource was started by the HAC automatically | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-07 05:26 | 2021-03-07 05:26 | 2021-03-07 05:26 | The resource was started by the HAC automatically | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T18 | C1G3A1B1C1 | fs_DEV_CI | FS main instance | 2021-03-07 05:33 | 2021-03-07 05:33 | 2021-03-07 05:56 | System failover. The node was fenced. | System failover | RG failover |  | System | 0:23 |  |  | 0:23 | 0:00 |  |  | 0:23 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T18 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-07 05:33 | 2021-03-07 05:33 | 2021-03-07 05:56 | System failover. The node was fenced. |  | No failure
T19 | C1G5A1B2 | fs_DEV_sapmnt | FS DLM | 2021-03-07 05:58 | 2021-03-07 06:00 | 2021-03-07 06:17 | System failover. The node was fenced. | System failover | No failure |  | System | 0:16 |  |  | 0:16 | 0:02 | 0:00 |  | 0:16 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T10 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-07 07:22 | 2021-03-07 07:24 | 2021-03-07 07:24 | 5 times between 07:22:09 and 07:23:47. The first ones were restarted by the application, and one restart by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:01 | 0:00 |  | 0:00 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T11 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-07 07:47 | 2021-03-07 07:48 | 2021-03-07 07:48 | Automatically restarted by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  | 0:00 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T12 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-07 07:54 | 2021-03-07 07:54 | 2021-03-07 08:12 | Resulting in failure of the node is fenced and complete system restart | System failover | RG failover |  | System | 0:18 |  |  | 0:18 | 0:00 | 0:00 |  | 0:18 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T13 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-07 08:15 | 2021-03-07 08:17 | 2021-03-07 08:17 | The resource is restarted by the HAC | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:01 | 0:00 |  | 0:00 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T13 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | [18 empty] | 0:00 |  | 0:00
T14 | C1G2A1B1C1 | fs_DEV_database | FS database | 2021-03-07 22:15 | 2021-03-07 22:18 | 2021-03-07 22:47 | System failover. The node was fenced. | System failover | RG failover |  | System | 0:30 |  |  | 0:30 | 0:03 |  |  | 0:30 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T15 | C1G3A1B1 | rsc_DEV_CI | main instance | 2021-03-07 22:59 | 2021-03-07 22:59 | 2021-03-07 23:15 | System failover. The node was fenced. | System failover | No failure |  |  | 0:16 | [9 empty] | 0:00 |  | 0:00
T15 | C1G3A1B1C1 | fs_DEV_CI | FS main instance | 2021-03-07 22:59 | 2021-03-07 22:59 | 2021-03-07 23:15 | System failover. The node was fenced. |  |  |  | System | 0:16 |  |  | 0:16 | 0:00 |  |  | 0:16 |  | 0:00 |  | 0:00 |  | 0:00
T16 | C1G1A1B1C1 | fs_DEV_ASCS | FS message and lock service | 2021-03-07 23:20 | 2021-03-07 23:20 | 2021-03-07 23:31 | System failover. The node was fenced. | System failover | RG failover |  | System | 0:11 |  |  | 0:11 | 0:00 |  |  | 0:11 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T16 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-07 23:20 | 2021-03-07 23:20 | 2021-03-07 23:31 | System failover. The node was fenced. |  | No failure | [12 empty] | 0:00 |  | 0:00
T17 | C1G1A1B1C2 | fs_2_DEV_ASCS | FS transport | 2021-03-07 23:33 | 2021-03-07 23:33 | 2021-03-07 23:33 | The resource was started by the HAC automatically | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:00 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T17 | C1G1A1B1C3 | fs_3_DEV_ASCS | FS interface | 2021-03-07 23:33 | 2021-03-07 23:33 | 2021-03-07 23:33 | The resource was started by the HAC automatically | No failure | No failure |  | Resource | 0:00 | 0:00 |  |  | 0:01 | 0:00 |  |  |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T18 | C1G3A1B1C1 | fs_DEV_CI | FS main instance | 2021-03-07 23:38 | 2021-03-07 23:39 | 2021-03-08 | System failover. The node was fenced. Both nodes were fenced one after another. | System failover | RG failover |  | System | 0:21 |  |  | 0:21 | 0:02 |  |  | 0:21 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
T18 | C1G1A1B1 | rsc_DEV_ASCS00 | message and lock service | 2021-03-07 23:37:47 | 2021-03-07 23:39 | 2021-03-08 | System failover. The node was fenced. Both nodes were fenced one after another. |  | RG failover
T19 | C1G5A1B2 | fs_DEV_sapmnt | FS DLM | 2021-03-07 06:53 | 2021-03-07 06:55 | 2021-03-07 07:12 | System failover. The node was fenced. | System failover | No failure |  | System | 0:17 |  |  | 0:17 | 0:02 |  |  | 0:17 |  | 0:00 | 0:00 | 0:00 | 0:00 | 0:00